## Millestone Plan
Milestone plan for the CSAM Prototype
Author: Tono
Planned date | Administration & Logistics | SAT path | STD path | Design | Test | Risk Analysis | Code | Milestone description | Task Responsible | Date: | Remarks
PHASE 1: DEFINITION & BASIC INSTALLATION (Alarm system and Network transmission)
[7 empty] | AL1 | Place ready for protoype
[7 empty] | AL2 | Material order sent for PHASE 1
[7 empty] | AL3 | Material for PHASE 1 received
[7 empty] | DES1 | Interface with Alarm system, Event Logging, Data Logging and Data Bases, document done
[7 empty] | SAT1 | Installation of SAT transmission equipment
[7 empty] | STD1 | Installation of STD transmission equipment
[7 empty] | DES2 | Interface with the Announciation Equipment, document done
[7 empty] | T1 | Prototype Test Plan document ready
[7 empty] | RA1 | Risk analysis's methodology approved by the enterprise
[7 empty] | SAT2 | Installation of SATalarm system
[7 empty] | STD2 | Installation of STD alarm system
[7 empty] | DES3 | Data to be transmitted defined
PHASE 2: ANNOUNCIATION EQUIPMENT & GLOBAL COMMISSIONING
[7 empty] | AL4 | Material order sent for PHASE 2
[7 empty] | RA2 | Risk analysis for CSAM prototype done
[7 empty] | SAT3 | Programation of SAT equipment done and tested
[7 empty] | AL5 | Material for PHASE 2 received
[7 empty] | STD3 | Programation of STD equipment done and tested
[7 empty] | SAT/STD4 | Installation of the Announciation Equipment done
[7 empty] | DES4 | Announciation Equipment views for the prototype defined
[7 empty] | SAT/STD5 | Progammation of the Announcaition Equipment done and tested
[7 empty] | DES5 | Prototype data introduced into the Data Bases
[7 empty] | T2 | Prototype Test Specifications done
[7 empty] | SAT/STD6 | Global commissioning done
[7 empty] | AL6 | Prototype accepted and ready for explotation
PHASE 3: TESTS & EXPLOTATION
[7 empty] | T3 | Prototype tests performed
[7 empty] | T4 | Analysis of the results
[7 empty] | T5 | Further tests
M2
M1
R3
R4
R3
V2
R4
R5
M4
P2
P3
R6
R2
R3
R4
R3
R4
R5
P2
P3
R6
R2
P2
P3
M3
AL1
AL2
AL3
T1
DES1
SAT1
STD1
DES2
RA1
SAT2
STD2
DES3
AL4
AL5
SAT3
STD3
SAT4
STD4
DES4
SAT5
STD5
DES5
SAT/STD6
T2
AL6
T3
T4
T5
RA2
DRAFT

## DL1-DL2-DL3
Prototype - Logistic DL1-DL2-DL3
[5 empty] | x execute the work D takes decision solely d takes decision jointly P manages progress T provides tuition on the job I must | Catherine | Tono | Frederic | David
Work content Days | Start Date | Period length : 1 week | Compl. Date
|  |  |  | Version 1.0 | Approved by
Week
|  |  |  | Code | Milestone
0

## DL4
Prototype - Data definition. DL4
[5 empty] | x execute the work D takes decision solely d takes decision jointly P manages progress T provides tuition on the job I must | Carlos | Silvia | Uwe | Bruno | Tono | Floris | Denis
Work content Days | Start Date | Period length : 1 week | Compl. Date
|  |  |  | Version 1.0 | Approved by
Week
|  |  |  | Code | Milestone
0

## DL5
Prototype - Definition view DL5
[5 empty] | x execute the work D takes decision solely d takes decision jointly P manages progress T provides tuition on the job I must | Carlos | Silvia | Tono | Peter | Uwe
Work content Days | Start Date | Period length : 1 week | Compl. Date
|  |  |  | Version 1.0 | Approved by
Week
|  |  |  | Code | Milestone
0

## DL6
Prototype - ELS DL6
[5 empty] | x execute the work D takes decision solely d takes decision jointly P manages progress T provides tuition on the job I must | Marius | Roberto | Tono | Uwe
Work content Days | Start Date | Period length : 1 week | Compl. Date
|  |  |  | Version 1.0 | Approved by
Week
|  |  |  | Code | Milestone
0

## DL7
Prototype - Test doc. DL7
[5 empty] | x execute the work D takes decision solely d takes decision jointly P manages progress T provides tuition on the job I must | Carlos | Silvia | Tono | Floris | Denis | Uwe | Frederic | David | Carmen | Peter
Work content Days | Start Date | Period length : 1 week | Compl. Date
|  |  |  | Version 1.0 | Approved by
Week
|  |  |  | Code | Milestone
0

## DL8
Prototype - Global test DL8
[5 empty] | x execute the work D takes decision solely d takes decision jointly P manages progress T provides tuition on the job I must | Carlos | Silvia | Tono | Floris | Denis | Uwe | Frederic | David | Carmen | Peter | Roberto
Work content Days | Start Date | Period length : 1 week | Compl. Date
|  |  |  | Version 1.0 | Approved by
Week
|  |  |  | Code | Milestone
0

## DL9
Prototype - Acceptance DL9
[5 empty] | x execute the work D takes decision solely d takes decision jointly P manages progress T provides tuition on the job I must | Carlos | Silvia | Tono | Floris | Denis | Uwe | Frederic | David | Carmen | Peter | Roberto
Work content Days | Start Date | Period length : 1 week | Compl. Date
|  |  |  | Version 1.0 | Approved by
Week
|  |  |  | Code | Milestone
0

## GSTD1-GSAT1-TSAT1
GSTD1-GSAT1-TSAT1
[5 empty] | x execute the work D takes decision solely d takes decision jointly P manages progress T provides tuition on the job I must | Floris | Denis | Frederic | David | Tono | Carmen
Work content Days | Start Date | Period length : 1 week | Compl. Date
|  |  |  | Version 1.0 | Approved by
Week
|  |  |  | Code | Milestone
0

## TSTD1-TSTD2
Prototype - Middleware STD
[5 empty] | x execute the work D takes decision solely d takes decision jointly P manages progress T provides tuition on the job I must | Roberto | Carmen | Tono | Bruno
Work content Days | Start Date | Period length : 1 week | Compl. Date
|  |  |  | Version 1.0 | Approved by
Week
|  |  |  | Code | Milestone
0

## TSAT2
Prototype - Middleware SAT
[5 empty] | x execute the work D takes decision solely d takes decision jointly P manages progress T provides tuition on the job I must | Floris | Denis | Frederic | David | Tono
Work content Days | Start Date | Period length : 1 week | Compl. Date
|  |  |  | Version 1.0 | Approved by
Week
|  |  |  | Code | Milestone
0

## SSTD1-SSTD2
Prototype - Supervision STD
[5 empty] | x execute the work D takes decision solely d takes decision jointly P manages progress T provides tuition on the job I must | Peter | Tono
Work content Days | Start Date | Period length : 1 week | Compl. Date
|  |  |  | Version 1.0 | Approved by
Week
|  |  |  | Code | Milestone
0

## SSAT1-SSAT2
Prototype - Supervision SAT
[5 empty] | x execute the work D takes decision solely d takes decision jointly P manages progress T provides tuition on the job I must | Tono | Peter
Work content Days | Start Date | Period length : 1 week | Compl. Date
|  |  |  | Version 1.0 | Approved by
Week
|  |  |  | Code | Milestone
0